## ScheduleV1.0_B2C
ORDEX Technology Solution Inc Emaster Project Schedule B2C
Milestone # | Milestone Deliverables(Form/Page) | Responsible | Dependency | Delivery Date | Tasks (Functionality) | Question | Additional Detail | Resource
M-0 | Requirement and Wireframe | ordex | None | Done | None | None | None | None
M-1 | Requirement Review & Clarification | Ordex | None | Done | None | None | None | None
M-2 | UI/UX Designed and Signed Off | Ordex | None | Done | 1. Home page(Campco,UZ,Humvee,Smith & Wesson,Recover Tactical,Swiss Tritium) 2. Shop Page. 3. product disciption. 4.Our Company 5. About Us 6. FAQ 7. Contact 8. Product catalog pages 9. Login page 10. Cart 11. Drop Shipping 12. Becoming a Dealer 13. Register 14. Customize your product feed page 15. Media Resources 16. Videos 17. Catalog | None | Static webPage Designed for emaster B2C | JaiminBhai
M-3 | DB Design | Ordex | M-0, M-1,M-2 | Done | None | None | DB Is Already Designed. But Somewhere May be need to change. | Nisha, harikirishna
M-4 | Admin Panel | Ordex | none | Done | None | None | Admin panel has been already Developed. | _
M-5 | B2C(Retail) Module. | ordex | none |  |  | None |  | Nisha, harikirishna
M-5.1 | Master Page(common content in all pages ) | Ordex | none | 1stweek, 2nd week | 1.show Campco logo. (by deafault content of campco brand) 2. show all brands of emaster. 3. all category of brands. 4.subcategory of particular category. 5. show top 6 brand logo. 6. Show brands in footer. 7. Show particular brand and discription in footer. 8. search product by product name. | 1. need category & subcategory in footer? 2. need to show contact us detail dyanamic? | Master page developed For Common content in Emaster B2C . | Nisha, harikirishna
M-5.2 | home Page | Ordex | M-5.1 | 2nd week | 1. Show top 10 product on home page. 2. show top 5 brand on home page. 3. show top 5 new product on home page. | 1. Fast Shipping Added dyanamic or static? 2. 1-Year Warranty added dynamic or statc? 3. No Middleman " " " " 4. Brands You Trust " " " " 5.Customer Service " " " " 6.Safe and Secure " " " " 7.dynamic image from database in primary slider? 8. dynamic image from database in scondry slider.? | None | Nisha, harikirishna
M-5.3 | product/ shop | Ordex | M-5.2 |  | 1. show all product by category selected from brand. 2. functionality for various sorting of product dropdown at left top corner. 3. functionality for filtering product by price at left top corder. 4. show top 3 product of below filter. 5. functionality for top rated product. | No | None | Nisha, harikirishna
M-5.4 | Product Detail | ordex | M-5.1, M-5.2 | 2nd week | 1. Show product images. 2. show product deatil as Name, price, category etc. 3. product discription. 4. show top 3 product realted to above product. | No | None | Nisha, harikirishna
M-5.5 | Cart | ordex | M-5.4 | 3rd week | 1. Add Products in cart. 2. functionality to change quantity. 3. apply coupon code. 4. proceed to checkout. 5. Add/ Remove product from cart. |  |  | Nisha, harikirishna
M-5.6 | Checkout | ordex | M-5.5, M-5.7,M-5.8 | 3rd week | 1. insert billing detail and additional detail. 2. show order deatil. 3. payment procedure. 4. place order. | No | None | Nisha, harikirishna
M-5.7 | Create Account/ registration | ordex | None | 4th week | 1. create registraion form for become user. | No | None | Nisha, harikirishna
M-5.8 | Login/ My Account | ordex | M-5.7 | 4th week | 1. Create login Form. | 1. Need To create forgot password Form?. | None | Nisha, harikirishna
M-5.9 | About us | ordex | None | 4th week | 1. Show Brand wise About Us. | 1. Need To create About Us Detail from database? 2. Need to show images from database in about us? | None | Nisha, harikirishna
M-5.10 | Contact us | ordex | none | 5th week | 1. add contact Deatil. 2. Show Contact address 3. To show content of our Strategy , our Company, our process. 4. to show content of Investor Realtions, Warrenty, returns & delivery, general-announcement | 1.To show content of our Strategy , our Company, our process from Database? 2. to show content of Investor Realtions, Warrenty, returns & delivery, general-announcement From Database? 3. to show Contact address From Database. | None | Nisha, harikirishna
M-5.11 | Brands | ordex | none | 5th week | 1. List of all Brands. | No | None | Nisha, harikirishna
M-5.12 | FAQ | ordex | none | 5th week | 1. Create FAQ form in aspx page. | FAQ Content Need dynamic? | None | Nisha, harikirishna
M-5.13 | Our Company | ordex | none. | 6th week | 1. To create our company Fom aspx | need To create Company Form content From Database 1.To show content of our Strategy , our Company, our process from Database? 2. to show content of Investor Realtions, Warrenty, returns & delivery, general-announcement From Database? 3. to show Contact address From Database. | None | Nisha, harikirishna
M-5.14 | Site Map | ordex | None | 6th week | 1. Add Sitemap functionality. | How added This Functionality? | None | Nisha, harikirishna
M-5.15 | Video | ordex | None | 6th week | 1. Add Video link for Yutube | How added This Functionality? | None | Nisha, harikirishna
M-5.16 | Media | ordex | None | 6th week | 1. Add Media Funcationality | How added This Functionality? | None | Nisha, harikirishna
M-5.17 | Carrier | ordex | None | 6th week | 1. Show Carrier related post in carrier Form. | 1. Show job post from Database? | None | Nisha, harikirishna

## Planning Sheet
Sr No | Page | HTML Link | B2B | B2C | W/O Login | Common | Describe if not Common
1 | Login | http://www.ordextechnology.com/campco/my-account.html | Y | Y
2 | Registration | http://www.ordextechnology.com/campco/registration.html | Y | N
3 | Home Page (Campco Brand) | http://www.ordextechnology.com/campco/index.html | Y | Y
4 | UZI Home Page | http://www.ordextechnology.com/campco/uzi.html | Y | Y
5 | humvee Home page | http://www.ordextechnology.com/campco/humvee.html | Y | Y
6 | Smith & Wesson(Home Page) | http://www.ordextechnology.com/campco/smith-wesson.html | Y | Y
7 | Recover Tactical(Home Page) | None | Y | Y
8 | Swiss Tritium(Home Page) | none | Y | Y
9 | Shop Page | http://www.ordextechnology.com/campco/shop.html | Y | Y
10 | Product Description page | http://www.ordextechnology.com/campco/products-details.html | Y | Y
11 | Our Company | http://www.ordextechnology.com/campco/our-company.html | Y | Y
12 | About Us | http://www.ordextechnology.com/campco/about-us.html | Y | Y
13 | FAQ | http://ordextechnology.com/campco/faq.html | Y | Y
14 | Contact | http://ordextechnology.com/campco/contact.html | Y | Y
15 | Cart | http://www.ordextechnology.com/campco/cart.html | Y | Y
16 | Becoming a Dealer | None | Y | N
17 | Media Resources | http://ordextechnology.com/campco/media.html | Y | Y
18 | Videos | http://ordextechnology.com/campco/video.html | Y | Y
19 | Checkout | http://www.ordextechnology.com/campco//checkout.html | Y | Y

## Sheet1
Common
ProductDetailPage | View=B2B¦B2C